## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Deepak Kumar Hota | 2025-12-05 | Backend API not returning diet recommendations correctly | Sprint 1 | Palak Komali | Functional | Fixed API response handling | 2025-12-06 | Closed | Verified with frontend
2 | Priya Mokkapati | 2025-12-05 | Frontend login page UI misalignment on mobile | Sprint 1 | Chhavi Subhash J | UI | Updated CSS & responsive layout | 2025-12-06 | Closed | Tested on Chrome & Firefox
3 | Venkata Arjun Rankela | 2025-12-06 | Fitness agent giving generic suggestions repeatedly | Sprint 1 | Sagar Gowd Yellu | Logic | Updated agent prompts and context handling | 2025-12-07 | Closed | Confirmed improved suggestions
4 | Harshitha Reddy | 2025-12-06 | Profile update API failing for weight field | Sprint 1 | Karthik Bhandarkar | Functional | Fixed field validation in backend | 2025-12-07 | Closed | All profile updates verified
5 | Ankitha B M | 2025-12-07 | Markdown not rendering properly in wellness plan | Sprint 1 | Hemangi Borase | UI | Corrected react-markdown usage | 2025-12-08 | Closed | Markdown now renders correctly
6 | Yarrappagari Snehalatha Reddy | 2025-12-08 | Follow-up Q&A context missing previous recommendations | Sprint 1 | Abhilash K R | Functional | Fixed session memory sharing | 2025-12-09 | Closed | Context now preserved
7 | Deepak Kumar Hota | 2025-12-09 | SSE streaming delays in frontend | Sprint 1 | Palak Komali | Performance | Optimized SSE handling | 2025-12-10 | Closed | Streaming response faster
8 | Priya Mokkapati | 2025-12-10 | Lifestyle agent returning incomplete advice | Sprint 1 | Chhavi Subhash J | Logic | Improved agent orchestration | 2025-12-11 | Closed | Validated against test cases
9 | Venkata Arjun Rankela | 2025-12-11 | User profile image upload failing | Sprint 1 | Sagar Gowd Yellu | Functional | Fixed file handling in backend | 2025-12-12 | Closed | Upload successful
10 | Harshitha Reddy | 2025-12-12 | Diet suggestions missing hydration tips | Sprint 1 | Karthik Bhandarkar | Functional | Updated diet agent outputs | 2025-12-13 | Closed | Verified hydration included

## Sheet2
Logical
User Interface
Maintainability
Standards
Others